## WBS with Gantt Chart EXAMPLE
Work Breakdown Structure With Gantt Chart Template Example
Project Title
Project Manager
Company Name
Date | [6 empty] | Phase One | [14 empty] | Phase Two | [14 empty] | Phase Three | [14 empty] | Phase Four
WBS Number | Task Title | Task Owner | Start Date | Due Date | Duration | % of Task Complete | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Leon W | 2055-03-12 | 2055-03-15 | 3 | 100% | bar: Week 2 M to Week 2 W
1.1.1 | Project Charter Revisions | Kylie R | 2055-03-15 | 2055-03-16 | 1 | 100% | bar: Week 2 W to Week 2 R
1.2 | Research | Pete S | 2055-03-15 | 2055-03-21 | 6 | 90% | bar: Week 2 W to Week 3 R
1.3 | Projections | Steve L | 2055-03-16 | 2055-03-22 | 6 | 40% | bar: Week 2 R to Week 3 R
1.4 | Stakeholders | Allen W | 2055-03-17 | 2055-03-22 | 5 | 70% | bar: Week 2 F to Week 3 R
1.5 | Guidelines | Malik M | 2055-03-18 | 2055-03-22 | 4 | 60% | bar: Week 3 M to Week 3 R
1.6 | Project Initiation | Malik M | 2055-03-23 | 2055-03-23 | 0 | 50% | bar: Week 3 F
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Steve L | 2055-03-24 | 2055-03-28 | 4 | 5% | bar: Week 4 M to Week 4 F
2.2 | Budget | Allen W | 2055-03-29 | 2055-04-02 | 4 | 30%
2.3 | Communication Plan | Malik M |  |  | 0 | 0%
2.4 | Risk Management | Malik M |  |  | 0 | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking | Pete S |  |  | 0 | 0%
3.2 | KPIs | Leon W |  |  | 0 | 0%
3.2.1 | Monitoring | Kylie R |  |  | 0 | 0%
3.2.2 | Forecasts | Kylie R |  |  | 0 | 0%
3.3 | Project Updates | Pete S |  |  | 0 | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  | 0 | 0%
4.2 | Quality Deliverables | Allen W |  |  | 0 | 0%
4.3 | Effort & Cost Tracking | Malik M |  |  | 0 | 0%
4.4 | Project Performance | Malik M |  |  | 0 | 0%
Formulas:
Duration = DAYS([Due Date],[Start Date])

## WBS with Gantt Chart BLANK
Work Breakdown Structure With Gantt Chart Template
Project Title
Project Manager
Company Name
Date | [6 empty] | Phase One | [14 empty] | Phase Two | [14 empty] | Phase Three | [14 empty] | Phase Four
WBS Number | Task Title | Task Owner | Start Date | Due Date | Duration | % of Task Complete | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%